Canada VHS Inventory Intake and Shopify Publishing System

Finalized Build Plan, Workflow, SOP, and Dependency-Aware Checklist

Version 2.0 — QR-Delimited Workflow

July 2026

Final operating decision: explicit QR item boundaries, local spreadsheet entry, and direct Shopify draft uploads from local images.

# Document Control

| Field | Value |
| --- | --- |
| Owner | Canada VHS |
| Primary operator | Isaiah Newman |
| Production computer | Linux Mint Mac |
| Development environment | Private GitHub repository and GitHub Codespaces |
| Storefront | Shopify |
| Status | Approved design; real production pilot pending |

Purpose of this revision. Replace the previous timestamp-gap design while retaining the current printed QR card set. The primary Shopify path is now a direct, controlled Admin API uploader that matches each Item ID to its local image files.

# Major Changes From Version 1.0

| Area | Version 2.0 decision |
| --- | --- |
| Grouping | Removed timestamp-gap grouping. CVHS1:ITEM:NEXT is the sole normal item boundary. |
| Existing cards | No new QR cards are required. The current card set remains valid. |
| CONT card | CVHS1:ITEM:CONT remains recognized for compatibility but performs no grouping action. |
| Photos | The first product photo is F (front). All additional photos are numbered 02, 03, 04, and so on. |
| Batch identity | The program generates the batch date/time and accepts an optional batch name such as COMEDY. |
| Human entry | The parser generates a local work CSV. Titles, prices, and other details are entered in batch order. |
| Shopify | A controlled uploader reads the work CSV, finds local photos by Item ID, creates Shopify drafts, and uploads images directly. |
| Hosting | No external image host and no public image URL are required for the primary workflow. |
| Bulk behavior | The program processes a whole selected batch automatically, while internally creating and verifying products in a controlled queue. |
| System of record | SQLite retains durable item, image, and Shopify IDs; CSV remains the convenient spreadsheet editing surface. |

# Current Project State

| Component | Status | Meaning |
| --- | --- | --- |
| Workflow and nomenclature | Complete | Final operating decisions are documented in this revision. |
| QR card vocabulary and PDF | Complete | Existing START, END, NEXT, CONT, RARE, REVIEW, shelf, and Q1 cards are retained. |
| QR parser prototype | Prototype complete | Synthetic tests using the actual QR cards passed; a real Pixel production batch remains required. |
| Physical shelf rollout | Pending verification | Shelves, labels, booth, and physical capacity must be completed and tested at home. |
| SQLite and spreadsheet round-trip | Planned | The parser output exists; durable database and re-import workflow remain to be built. |
| Direct Shopify uploader | Planned | This is the next major software deliverable. |
| AI recognition and pricing | Deferred | Not required to clear the current backlog. |

# Part I — Finalized System Plan

## 1. Objective

Build a low-cost, high-throughput intake system that preserves an unbroken link between each physical VHS, its shelf location, its local record, its photographs, and its Shopify draft. The system eliminates individual tape labeling and manual photo matching while remaining simple enough for one technically capable owner to operate.

## 2. Final Architecture

Pixel camera photos + current QR cards
        ↓
Chronological EXIF sorting
        ↓
QR state-machine parser
        ↓
Grouped and renamed local images
        ↓
SQLite records + inventory_work.csv
        ↓
Manual title/price entry in batch order
        ↓
Validation / dry run
        ↓
Controlled Shopify uploader
        ↓
Draft product + variant + inventory + local images
        ↓
Human Shopify review and publication

No external static image host is required. The work CSV links to local Item IDs and folders; the uploader sends the matching local files directly to Shopify.

## 3. Physical Inventory Model

Shelves use the existing A1–J10 and Q1 codes.

Individual tapes are not labeled.

The shelf code is the maintained physical location.

The batch sequence is an intake and pick hint, not a permanent exact slot after sales and shelf changes.

Listed shelves are controlled warehouse stock, not casual browsing shelves.

Q1 is quarantine for mold, damage, testing, or uncertainty.

Dividers every 25–30 tapes are optional; a shelf may hold roughly 50–100 tapes when visual searching remains practical.

### Duplicate handling

Pooled copies: same edition and comparable condition; any qualifying copy can fulfil the listing.

Unique copies: rare, sealed, screener, signed, unusual packaging, collectible Canadian issue, or materially different condition. Exact-copy photographs remain tied to the item.

## 4. Existing QR Cards and Final Meaning

| Printed card | QR payload | Program behavior | Operator rule |
| --- | --- | --- | --- |
| START NEW BATCH | CVHS1:BATCH:START | Starts the command stream. Photograph first. | Required once per session. |
| END BATCH | CVHS1:BATCH:END | Finalizes the open item and ignores later photos. | Required once per session. |
| NEXT VHS TAPE | CVHS1:ITEM:NEXT | Closes the current item. The next ordinary photo begins the next item. | Primary item delimiter; use between every VHS. |
| MORE PHOTOS — SAME VHS | CVHS1:ITEM:CONT | Compatibility no-op. Photos already remain with the current item until NEXT. | Keep the existing card; do not use in normal operation. |
| RARE / UNIQUE NEXT VHS | CVHS1:FLAG:RARE | Flags the next item as exact-copy / non-pooled. | Scan after NEXT and before the item front. |
| REVIEW NEXT VHS | CVHS1:FLAG:REVIEW | Flags the next item for manual review. | Can be combined with RARE. |
| SHELF A1–J10 | CVHS1:LOC:<CODE> | Sets the active physical shelf for following items. | Scan only between items. |
| QUARANTINE Q1 | CVHS1:LOC:Q1 | Sets the active location to quarantine. | Use for mold, damage, testing, or uncertainty. |

### Parser state rule

All ordinary photos belong to the current item until CVHS1:ITEM:NEXT is photographed. The first ordinary photo after START and shelf setup begins item 001. NEXT closes the current item; the next ordinary photo begins the next item. A trailing NEXT before END does not create an empty item.

START
SHELF B2
Item 001: front, back, open
NEXT
Item 002: front
NEXT
RARE
REVIEW
Item 003: front, back, tape
END

## 5. Photography Rules

1. Photograph START first.

2. Photograph the active shelf card.

3. Photograph the first VHS front first.

4. Take any number of additional photographs before NEXT.

5. Photograph NEXT after finishing the item and before the next item.

6. Photograph RARE and/or REVIEW after NEXT and before the flagged item front.

7. Photograph a new shelf card only between items.

8. Photograph END last.

The first product image is always the front. Additional images have no mandatory semantic order and are simply numbered. Open-case or reel photographs may take any amount of time because time gaps do not create boundaries.

## 6. Batch, Item, and File Nomenclature

### Batch ID

YYYYMMDD-HHMMSS[-BATCH-NAME]

20260715-143218-COMEDY
20260715-143218

The system generates the date and time when the batch is first imported. The optional name is sanitized to uppercase letters, numbers, and dashes. The identity is stored in batch_manifest.json and reused on reprocessing.

### Item ID and Shopify SKU

<BATCH-ID>-<SHELF>-<ITEM>

20260715-143218-COMEDY-B2-023

### Photo names

20260715-143218-COMEDY-B2-023-F.jpg
20260715-143218-COMEDY-B2-023-02.jpg
20260715-143218-COMEDY-B2-023-03.jpg

The movie title is not part of the authoritative filename. Titles can be corrected without breaking the file-to-item relationship.

## 7. Output Structure

CanadaVHS/data/
├── incoming/<source-session>/
├── originals/<batch-id>/
├── processed/<batch-id>/images/
├── processed/<batch-id>/commands/
├── processed/<batch-id>/batch_manifest.json
├── processed/<batch-id>/image_manifest.csv
├── processed/<batch-id>/commands.csv
├── processed/<batch-id>/inventory_work.csv
├── processed/<batch-id>/warnings.txt
├── database/inventory.sqlite3
├── exports/
└── backups/

## 8. Human Spreadsheet Workflow

inventory_work.csv is the fast human editing surface, not the Shopify image importer. It contains one row per item and is keyed by Item ID. The operator types titles and prices in the same sequence as the physical shelf and parser output.

Item ID / SKU

Batch ID

Shelf and sequence

Rare and review flags

Title and price

Description, vendor, type, and tags

Barcode and condition

Quantity

Local image folder and image count

Ready and upload status

Shopify product, variant, inventory item IDs, and admin URL

Last error and retry count

When the CSV is imported back, the program updates records by Item ID only. It never links data by title or spreadsheet row position.

## 9. Direct Shopify Upload Workflow

1. Read all items marked READY.

2. Validate title, price, unique SKU, quantity, local images, and target Shopify location.

3. Check local records and Shopify for an existing SKU.

4. Create a Shopify product as DRAFT through the current GraphQL Admin API.

5. Configure the default variant, SKU, price, barcode, tax/shipping settings, and inventory tracking.

6. Set quantity at the configured Shopify inventory location.

7. Request staged upload targets.

8. Upload each local file and attach it to the correct product in F, 02, 03 order.

9. Verify media processing and image count.

10. Save Shopify IDs and admin URL immediately.

11. Continue automatically to the next item.

12. Produce a success/failure report and allow retry of failures only.

This behaves like a batch listing bot to the operator, but it uses Shopify’s authorized Admin API. Version 1 uses a controlled product queue rather than asynchronous JSONL bulk operations.

## 10. Data Authority and Safety

SQLite is the durable record of batches, items, photos, and Shopify IDs.

CSV is an import/export editing surface.

Shopify is the sales channel and published catalog.

Original images are never overwritten.

Shopify upload copies have GPS metadata removed.

Draft creation is idempotent: reruns skip successful items.

Publishing remains manual until the system is proven.

## 11. Condition Grades

| Grade | Definition |
| --- | --- |
| Fair | Complete and usable, but with substantial cosmetic wear or damage that is clearly disclosed. |
| Good | Normal used wear; artwork and case remain presentable and functional. |
| Very Good | Light wear only; clean and clearly above an average used copy. |
| Like New | Minimal visible handling wear; not represented as factory sealed. |
| Sealed | Factory seal appears intact; exact-copy photographs are required. |
| Damaged | Sellable only with specific damage disclosure or routed to review. |
| Mold Review | Potential contamination; must remain in Q1 and cannot be listed until cleared. |

## 12. Version-One Exclusions

New or redesigned QR cards

Timestamp-gap grouping

External static image hosting

Shopify product CSV as the primary upload path

Native Android application

AI-required identification

eBay sold scraping or public price graphs

Exact permanent slot numbering

Individual tape labels

Automatic publication

True Shopify bulkOperation import unless the controlled queue is later measured as too slow

# Part II — Standard Operating Procedure

## SOP 1 — Pre-Session

1. Confirm the Pixel clock is correct.

2. Clean the lens and booth surface.

3. Confirm battery, storage, lighting, and camera framing.

4. Confirm the destination shelf has capacity.

5. Separate unprocessed tapes from completed tapes.

6. Put START, END, NEXT, RARE, REVIEW, CONT, and required shelf cards beside the booth. CONT is retained but is not needed.

## SOP 2 — Start the Session

1. Photograph START.

2. Photograph the destination shelf QR.

3. Place the first tape in the standard position.

4. Photograph the front first.

## SOP 3 — Normal Item

1. Photograph the front.

2. Take any optional views: back, spine, open case, tape, reel, inserts, or damage.

3. Place the tape on the active shelf in intake order.

4. Photograph NEXT.

5. Prepare the next tape.

NEXT must occur after all photographs of the completed item and before the first photograph of the next item. Time between photographs is irrelevant.

## SOP 4 — Rare or Review Item

1. Finish the preceding item and photograph NEXT.

2. Photograph RARE and/or REVIEW.

3. Photograph the item front first and all needed exact-copy details.

4. Place the item on the active shelf or Q1 as appropriate.

5. Photograph NEXT before another item.

## SOP 5 — Shelf Change

1. Finish the current item.

2. Photograph NEXT.

3. Photograph the new shelf QR.

4. Photograph the next item front.

5. Never photograph a shelf command in the middle of one item’s product photos.

## SOP 6 — End and Transfer

1. After the final product photographs, photograph END. A trailing NEXT is optional and unnecessary.

2. Confirm every photographed tape was physically shelved.

3. Transfer the complete camera session to a new incoming folder.

4. Do not delete phone photos until originals, manifests, parser output, and a backup are verified.

## SOP 7 — Parse and Edit

1. Run parser dry-run.

2. Confirm START, shelf, NEXT count, flags, END, group count, and warnings.

3. Run write mode.

4. Open inventory_work.csv or the review interface.

5. Enter titles and prices in batch order.

6. Complete required fields and mark items READY.

7. Re-import and validate the edited CSV.

## SOP 8 — Upload to Shopify

1. Create a database backup.

2. Run Shopify dry-run validation.

3. Resolve all blocked rows.

4. Start upload of READY items.

5. Review progress and retry temporary failures.

6. Open the created drafts and verify title, price, images, SKU, and quantity.

7. Publish only after human review.

## SOP 9 — Picking and Location Errors

1. Open the local or Shopify record and note shelf and front photo.

2. Search the assigned shelf visually.

3. For a unique item, compare exact wear and packaging details.

4. If missing, inspect adjacent shelves, Q1, returns, and recent transfers.

5. Mark Location Review and audit the shelf before substituting or cancelling.

# Part III — Software Build Work Order

## Phase 0 — Freeze the Operating Method

### Work

[ ] Adopt this Version 2.0 plan as the current baseline.

[ ] Do not redesign or reprint the current QR card set.

[ ] Use NEXT between every item; do not use timestamp gaps for grouping.

[ ] Run one real 20-tape Pixel batch before expanding scope.

### Acceptance criteria

The operator can explain the workflow without reference to timing rules.

The actual QR cards decode correctly from real booth photos.

All 20 physical tapes can be matched to parser groups.

## Phase 1 — Local and Remote Development Setup

### Work

[ ] Create or confirm a private GitHub repository and Codespace.

[ ] Prepare the Linux Mint production machine, Python virtual environment, and data folders.

[ ] Move the current parser project into version control.

[ ] Keep production images, databases, and secrets out of Git.

### Acceptance criteria

The same code runs in Codespaces and on Linux Mint.

A test suite can be executed in both environments.

The production data directory is separate from the repository.

## Phase 2 — Harden the Existing Parser

### Work

[ ] Use EXIF capture time only to restore chronological order.

[ ] Use QR NEXT as the only normal item boundary.

[ ] Retain CONT as a logged no-op.

[ ] Generate stable batch, item, and image names.

[ ] Preserve originals and generate manifests.

[ ] Add resumability, duplicate-file detection, and clear warnings.

### Acceptance criteria

A real batch parses identically on repeated runs.

No original photo is changed.

Every ordinary photo belongs to exactly one item.

Command photos never become product images.

## Phase 3 — Database and Work CSV

### Work

[ ] Create SQLite tables for batches, items, photos, flags, and upload results.

[ ] Generate one inventory_work.csv row per item.

[ ] Allow the edited CSV to be imported back by Item ID.

[ ] Keep image_manifest.csv as one row per photo.

[ ] Validate titles, prices, SKUs, and local image presence.

### Acceptance criteria

CSV edits update the correct records without title-based matching.

Reimporting the same CSV is idempotent.

Every item can be opened with its associated local images.

## Phase 4 — Direct Shopify Draft Uploader

### Work

[ ] Create a Shopify custom app and obtain minimum required Admin API scopes.

[ ] Build dry-run validation.

[ ] Create products as drafts through the current GraphQL Admin API.

[ ] Upload local images through Shopify staged uploads and attach them to the correct product.

[ ] Configure SKU, price, barcode, inventory tracking, quantity, and location.

[ ] Save Shopify IDs and admin URLs immediately.

[ ] Verify media count and support safe retry.

### Acceptance criteria

A ten-item batch creates ten correct Shopify drafts.

No external image host is used.

Rerunning the uploader does not duplicate successful items.

A failed product can be retried independently.

## Phase 5 — Lightweight Review Interface

### Work

[ ] Add a Streamlit batch dashboard.

[ ] Show front image, optional images, title, price, shelf, flags, and status.

[ ] Add import, edit, validate, upload, retry, and open-in-Shopify actions.

[ ] Keep CSV import/export available for spreadsheet-speed editing.

### Acceptance criteria

The complete workflow can be operated without terminal commands.

A batch can be stopped and resumed without losing progress.

## Phase 6 — Production Pilot

### Work

[ ] Process 20 real tapes, correct defects, then process 100 real tapes.

[ ] Create Shopify drafts and perform random physical retrieval tests.

[ ] Measure photography, entry, upload, and pick time.

[ ] Document every mismatch and failure.

### Acceptance criteria

Zero physical-to-digital mismatches.

Every uploaded draft has the correct images and SKU.

Ten random tapes are retrieved successfully.

The workflow is materially faster than manual Shopify listing.

## Phase 7 — Deferred Automation

### Work

[ ] Add barcode/OCR/vision suggestions only after the manual workflow is stable.

[ ] Add existing-listing matching and duplicate pooling cautiously.

[ ] Evaluate true Shopify bulk operations only if the controlled queue becomes too slow.

[ ] Evaluate pricing research and eBay tools separately.

### Acceptance criteria

Automation reduces measured labour without increasing listing or location errors.

# Part IV — Dependency-Aware Implementation Checklist

Status: [ ] not started, [~] in progress, [x] complete, [!] blocked, [-] excluded. Sizes: XS under 15 minutes, S 15–60 minutes, M 1–3 hours, L 3–8 hours, XL over 8 hours. Begin a task only after all listed prerequisites are complete.

## Track A — Scope and Decisions

| Status | ID | Task | Size | Prerequisites | Done when |
| --- | --- | --- | --- | --- | --- |
| [ ] | A-01 | Save Version 2.0 as the active project baseline | XS | — | The file is stored in the repository and local project folder. |
| [ ] | A-02 | Record the final objective and success measures | S | A-01 | The target includes throughput, zero linkage loss, and successful retrieval. |
| [ ] | A-03 | Freeze the QR vocabulary | XS | A-01 | The existing card payloads are listed exactly; no new cards are required. |
| [ ] | A-04 | Freeze the batch nomenclature | XS | A-01 | YYYYMMDD-HHMMSS plus optional sanitized name is documented. |
| [ ] | A-05 | Freeze the item and photo nomenclature | XS | A-04 | Item ID and F/02/03 photo naming are documented. |
| [ ] | A-06 | Define required CSV fields | S | A-02,A-05 | One-row-per-item work CSV fields are approved. |
| [ ] | A-07 | Define Shopify draft defaults | S | A-02 | Vendor, type, tags, draft status, quantity, tax, and shipping defaults are recorded. |
| [ ] | A-08 | Define condition grades | S | A-02 | Every allowed condition has a written definition. |
| [ ] | A-09 | Define unique versus pooled inventory rules | M | A-08 | Rare, sealed, variant, and condition exceptions are explicit. |
| [ ] | A-10 | Define version-one exclusions | S | A-01 | AI, eBay scraping, external hosting, true bulk ops, and auto-publish are deferred. |

## Track P — Physical Space and Photography

| Status | ID | Task | Size | Prerequisites | Done when |
| --- | --- | --- | --- | --- | --- |
| [ ] | P-01 | Measure available walls and existing shelf capacity | M | — | Dimensions and approximate capacities are recorded. |
| [ ] | P-02 | Estimate the current unlisted tape count | M | — | A rough backlog quantity is recorded. |
| [ ] | P-03 | Calculate required capacity with growth space | S | P-01,P-02 | Planned capacity includes at least 20% free space. |
| [ ] | P-04 | Purchase suitable shelving and anchors | M | P-03 | Shelves and safety hardware are obtained. |
| [ ] | P-05 | Install and secure shelving | L | P-04 | Shelving is stable, level, and safely anchored where needed. |
| [ ] | P-06 | Assign physical shelf codes that match existing QR cards | S | P-05,A-03 | Every active shelf has one A1–J10 or Q1 code. |
| [ ] | P-07 | Attach large human-readable shelf labels | S | P-06 | Each shelf is readable without scanning. |
| [ ] | P-08 | Designate incoming and processed zones | S | P-05 | Unprocessed and completed tapes cannot mix. |
| [ ] | P-09 | Designate Q1 quarantine | XS | P-05 | Potential mold/damage items have a separate controlled area. |
| [ ] | P-10 | Set up the photo booth and plain background | M | — | The booth provides a consistent, uncluttered image. |
| [ ] | P-11 | Install lighting and reduce glare | M | P-10 | Glossy covers remain readable in test photos. |
| [ ] | P-12 | Install a phone mount and charging cable | M | P-10 | The Pixel can remain fixed and powered. |
| [ ] | P-13 | Add a repeatable tape placement guide | S | P-10 | Front images are framed consistently. |
| [ ] | P-14 | Place the current QR cards within easy reach | S | P-10,A-03 | START, END, NEXT, RARE, REVIEW, CONT, and active shelf cards are accessible. |
| [ ] | P-15 | Run a physical retrieval test with 50–100 tapes on one shelf | M | P-06 | A tape can be found from shelf code and photo without individual labels. |

## Track E — Development Environments

| Status | ID | Task | Size | Prerequisites | Done when |
| --- | --- | --- | --- | --- | --- |
| [ ] | E-01 | Confirm personal GitHub access and enable two-factor authentication | S | — | Personal account is secured and recovery codes are stored. |
| [ ] | E-02 | Create or confirm a private repository | S | E-01 | Repository is private and owned by the user. |
| [ ] | E-03 | Create a Codespace | S | E-02 | Browser VS Code and terminal open successfully. |
| [ ] | E-04 | Add README, LICENSE decision, and project status | S | E-02 | Repository explains purpose, setup, and data restrictions. |
| [ ] | E-05 | Create a production-safe .gitignore | S | E-02 | Images, databases, exports, .env, and secrets are excluded. |
| [ ] | E-06 | Create .env.example | XS | E-02 | Required Shopify and data-path variables are documented without secrets. |
| [ ] | E-07 | Back up the Linux Mint Mac | M | — | Important existing files have a separate copy. |
| [ ] | E-08 | Update Linux Mint and check disk health/free space | M | E-07 | OS is current and storage condition is acceptable. |
| [ ] | E-09 | Install Git, Python, venv, pip, and build tools | S | E-08 | Version commands succeed. |
| [ ] | E-10 | Create the CanadaVHS data directory tree | S | E-09 | Incoming, originals, processed, exports, database, backups, and logs exist. |
| [ ] | E-11 | Clone the repository on Linux Mint | S | E-02,E-09 | Local repository can pull and push. |
| [ ] | E-12 | Create virtual environments in Codespaces and Linux Mint | M | E-03,E-11 | Both environments install the same requirements. |
| [ ] | E-13 | Add pytest and lint commands | S | E-12 | Tests and linter run from one documented command. |
| [ ] | E-14 | Commit the current parser project and test fixtures | M | E-05,E-12 | The synthetic-tested parser is version controlled. |

## Track Q — Existing QR Card Compatibility

| Status | ID | Task | Size | Prerequisites | Done when |
| --- | --- | --- | --- | --- | --- |
| [ ] | Q-01 | Store the current QR card PDF and source assets | S | E-02 | The existing card set can be reprinted without redesign. |
| [ ] | Q-02 | Create an exact command allowlist in code | S | A-03 | Only the current CVHS1 payloads can change parser state. |
| [ ] | Q-03 | Implement START behavior | S | Q-02 | The first START opens the session; duplicates warn without resetting data. |
| [ ] | Q-04 | Implement END behavior | S | Q-02 | END finalizes the open item and excludes later ordinary photos. |
| [ ] | Q-05 | Implement NEXT as the sole item delimiter | M | Q-02 | Every ordinary photo between NEXT commands belongs to one item. |
| [ ] | Q-06 | Retain CONT as a compatibility no-op | S | Q-02 | Scanning CONT does not split, merge, or corrupt a group. |
| [ ] | Q-07 | Implement RARE and REVIEW as one-item pending flags | M | Q-02 | Flags can stack and reset after the next item begins. |
| [ ] | Q-08 | Implement shelf and Q1 state | M | Q-02 | The next item inherits the active location until changed. |
| [ ] | Q-09 | Warn when shelf/flag commands are used mid-item | S | Q-07,Q-08 | The parser logs the issue and applies changes only to the next item. |
| [ ] | Q-10 | Photograph-test every command type with the real Pixel booth | M | P-10,Q-02 | All command types decode in real conditions. |

## Track I — Image Import and Parser Hardening

| Status | ID | Task | Size | Prerequisites | Done when |
| --- | --- | --- | --- | --- | --- |
| [ ] | I-01 | Enumerate supported image files | S | E-14 | JPG/JPEG/PNG and planned HEIC behavior are explicit. |
| [ ] | I-02 | Read EXIF DateTimeOriginal and subsecond data | M | I-01 | Pixel images return capture order metadata. |
| [ ] | I-03 | Add deterministic timestamp fallbacks | M | I-02 | Missing EXIF falls back with a warning, never silently. |
| [ ] | I-04 | Sort the entire command stream oldest-first | M | I-02,I-03 | Repeated runs produce the same chronological order. |
| [ ] | I-05 | Support optional newest-first final item numbering | S | I-04 | Commands still parse chronologically; only final numbering can reverse. |
| [ ] | I-06 | Generate batch ID from system date/time | M | A-04 | A new batch receives YYYYMMDD-HHMMSS. |
| [ ] | I-07 | Accept and sanitize an optional batch name | S | I-06 | Comedy / 80s Comedy become safe uppercase tokens. |
| [ ] | I-08 | Persist batch identity in batch_manifest.json | M | I-06,I-07 | Rerunning the same imported batch reuses the original ID. |
| [ ] | I-09 | Generate immutable Item IDs | M | A-05,I-08 | Each item receives batch-shelf-sequence identity. |
| [ ] | I-10 | Name first photo F and additional photos 02+ | M | I-09 | No optional image role is guessed. |
| [ ] | I-11 | Copy originals without modification | M | E-10,I-04 | Source hashes remain unchanged. |
| [ ] | I-12 | Generate processed copies and thumbnails | M | I-11 | Review and upload copies are reproducible from originals. |
| [ ] | I-13 | Strip GPS metadata from Shopify upload copies | M | I-12 | Public media contains no precise capture location. |
| [ ] | I-14 | Calculate file hashes | M | I-01 | Duplicate files can be detected. |
| [ ] | I-15 | Prevent duplicate imports | M | I-14 | Reimport requires explicit override or is skipped. |
| [ ] | I-16 | Generate image_manifest.csv | M | I-09,I-10 | Every image row links original path, new filename, item, and order. |
| [ ] | I-17 | Generate commands.csv and warnings.txt | M | Q-03,Q-09 | Every QR event and parser warning is traceable. |
| [ ] | I-18 | Add dry-run preview | M | I-16,I-17 | Parser shows groups and names without writing output. |
| [ ] | I-19 | Add safe write mode and collision protection | M | I-18 | Existing outputs are not overwritten silently. |
| [ ] | I-20 | Add resumability and clean failure recovery | L | I-19 | Interrupted processing can continue without duplicate outputs. |

## Track D — SQLite and Work CSV

| Status | ID | Task | Size | Prerequisites | Done when |
| --- | --- | --- | --- | --- | --- |
| [ ] | D-01 | Design batches, items, photos, commands, uploads, and settings tables | L | A-06,I-09 | Schema and relationships are documented. |
| [ ] | D-02 | Create database initialization and migration framework | L | D-01 | A new database and future upgrades are repeatable. |
| [ ] | D-03 | Import parser manifests into SQLite transactionally | L | D-02,I-16 | A batch either commits fully or not at all. |
| [ ] | D-04 | Create inventory_work.csv with one row per item | M | A-06,D-03 | Rows are sorted in physical batch order. |
| [ ] | D-05 | Include Item ID, shelf, sequence, flags, title, price, and local image folder | M | D-04 | The spreadsheet contains all manual-entry and linkage fields. |
| [ ] | D-06 | Include Shopify defaults and status fields | M | A-07,D-04 | Vendor, type, tags, quantity, draft status, and upload status are present. |
| [ ] | D-07 | Add Shopify ID and error columns | S | D-04 | Product, variant, inventory item, admin URL, error, and retry count can be recorded. |
| [ ] | D-08 | Build CSV re-import keyed only by Item ID | L | D-04 | Titles and prices update the correct records regardless of row movement. |
| [ ] | D-09 | Reject duplicate or unknown Item IDs | M | D-08 | Bad spreadsheet rows cannot update the wrong product. |
| [ ] | D-10 | Validate price, title, quantity, barcode, and required images | L | D-08 | Ready status is blocked until required data passes. |
| [ ] | D-11 | Add controlled condition values | M | A-08,D-08 | Condition cannot drift into inconsistent free-text values. |
| [ ] | D-12 | Add pooled versus unique choice | M | A-09,D-08 | Rare/unique records cannot be merged automatically. |
| [ ] | D-13 | Create shelf manifest export | M | D-03 | Each shelf has a printable/digital inventory list. |
| [ ] | D-14 | Create emergency CSV/Excel export | M | D-03 | Data can be audited outside the application. |
| [ ] | D-15 | Back up the database before every import and upload run | M | D-02 | A timestamped rollback point is created automatically. |

## Track S — Shopify Direct Uploader

| Status | ID | Task | Size | Prerequisites | Done when |
| --- | --- | --- | --- | --- | --- |
| [ ] | S-01 | Confirm Shopify plan/admin permissions allow custom app use | S | — | The user can create and manage an Admin API app. |
| [ ] | S-02 | Create a Shopify custom app for Canada VHS | M | S-01 | A private app exists in the store admin. |
| [ ] | S-03 | Grant minimum required product, file/media, inventory, and location scopes | M | S-02 | The app has no unnecessary access. |
| [ ] | S-04 | Store store domain and token in .env / Codespaces secrets | S | E-06,S-03 | Secrets are absent from Git and logs. |
| [ ] | S-05 | Build a read-only connection and shop identity test | M | S-04 | The program confirms it is connected to the correct store. |
| [ ] | S-06 | Query and select the Shopify inventory location | M | S-05 | The target location ID is stored in settings. |
| [ ] | S-07 | Create uploader dry-run validation | L | D-10,S-05 | A batch can be classified ready, blocked, or already uploaded without writes. |
| [ ] | S-08 | Check Shopify for an existing SKU before creation | L | S-05,D-07 | Duplicate creation is blocked. |
| [ ] | S-09 | Create one draft product through the current GraphQL Admin API | L | S-07,S-08 | Title, description, vendor, type, tags, and draft state are correct. |
| [ ] | S-10 | Configure the default variant | L | S-09 | SKU, price, barcode, taxable/shipping settings, and tracking are correct. |
| [ ] | S-11 | Set inventory quantity at the selected location | L | S-06,S-10 | Available quantity matches the local record. |
| [ ] | S-12 | Request staged upload targets for local images | L | S-05,I-12 | Shopify returns valid upload targets. |
| [ ] | S-13 | Upload local files to the staged targets | L | S-12 | Every local image upload completes successfully. |
| [ ] | S-14 | Attach uploaded media to the correct product in order | L | S-09,S-13 | F is first and numbered images follow. |
| [ ] | S-15 | Poll/verify media processing and image count | L | S-14 | The expected number of images is ready on the product. |
| [ ] | S-16 | Save Shopify IDs immediately after each successful step | M | S-09,S-10,S-11,S-14 | A restart can resume from the correct stage. |
| [ ] | S-17 | Generate a direct Shopify admin URL | S | S-16 | The user can open the new draft from the local record. |
| [ ] | S-18 | Implement one-product controlled queue | L | S-07,S-16 | A selected batch processes automatically without manual intervention per item. |
| [ ] | S-19 | Add adaptive throttling using Shopify query-cost responses | L | S-18 | The uploader pauses rather than failing under API limits. |
| [ ] | S-20 | Add bounded retry for temporary network/API failures | L | S-18 | Retries stop after a defined limit and preserve the last error. |
| [ ] | S-21 | Skip successful products on rerun | M | S-16,S-18 | The uploader is idempotent. |
| [ ] | S-22 | Add retry-selected-failures mode | M | S-20 | Only failed items can be retried. |
| [ ] | S-23 | Create batch upload results CSV/report | M | S-18 | Success, failure, IDs, URLs, and timestamps are exportable. |
| [ ] | S-24 | Keep publishing manual | S | S-09 | Uploader creates drafts only; no automatic storefront publication. |

## Track U — Local Review Interface

| Status | ID | Task | Size | Prerequisites | Done when |
| --- | --- | --- | --- | --- | --- |
| [ ] | U-01 | Create a Streamlit home/status page | M | E-12,D-03 | App shows data path, database, last backup, and current version. |
| [ ] | U-02 | Create batch import page | L | I-20,D-03 | A source folder can be selected and parsed without terminal use. |
| [ ] | U-03 | Create group thumbnail overview | L | D-03 | Every item shows F and optional images, shelf, flags, and Item ID. |
| [ ] | U-04 | Create spreadsheet-style item editor | L | D-08 | Title, price, barcode, condition, description, and tags can be edited. |
| [ ] | U-05 | Add CSV export/import buttons | M | D-04,D-08 | Spreadsheet workflow remains available. |
| [ ] | U-06 | Add ready/blocked filters | M | D-10 | Incomplete products are easy to isolate. |
| [ ] | U-07 | Add validate batch button | M | S-07 | Validation results are visible before upload. |
| [ ] | U-08 | Add upload selected / upload ready button | L | S-18 | The user can launch the controlled queue. |
| [ ] | U-09 | Show live progress and per-item status | L | S-18 | Current item, completed count, and failures are visible. |
| [ ] | U-10 | Add retry failures button | M | S-22 | Failed items can be retried without command line. |
| [ ] | U-11 | Add open image folder and open Shopify draft links | M | S-17 | Local and Shopify records are one click away. |
| [ ] | U-12 | Add safe resume after browser/app restart | L | D-03,S-16 | No completed review or upload progress is lost. |

## Track T — Testing and Acceptance

| Status | ID | Task | Size | Prerequisites | Done when |
| --- | --- | --- | --- | --- | --- |
| [ ] | T-01 | Maintain unit tests for chronological sorting | M | I-04 | Known metadata sequences always produce known order. |
| [ ] | T-02 | Test every current QR command with actual card images | M | Q-10 | All current cards decode and produce expected state. |
| [ ] | T-03 | Test one-photo through six-photo items | M | I-10,Q-05 | Variable image counts remain correctly grouped. |
| [ ] | T-04 | Test consecutive NEXT cards | S | Q-05 | No empty product is created; a warning is logged. |
| [ ] | T-05 | Test START/END duplicates and photos after END | S | Q-03,Q-04 | Parser remains safe and auditable. |
| [ ] | T-06 | Test RARE, REVIEW, and both flags together | S | Q-07 | Flags apply to exactly one intended item. |
| [ ] | T-07 | Test shelf changes and Q1 | S | Q-08,Q-09 | Items receive correct locations. |
| [ ] | T-08 | Test CONT no-op behavior | S | Q-06 | The command changes no grouping state. |
| [ ] | T-09 | Test missing EXIF and identical timestamps | M | I-03,I-04 | Fallback order is deterministic and warned. |
| [ ] | T-10 | Test duplicate import and filename collision | M | I-15,I-19 | No duplicate record or overwrite occurs. |
| [ ] | T-11 | Test CSV row reordering | M | D-08,D-09 | Item ID prevents mismatched updates. |
| [ ] | T-12 | Test invalid title, price, barcode, quantity, and missing image | M | D-10 | Every invalid item is blocked with a useful message. |
| [ ] | T-13 | Test Shopify dry run against real store | M | S-07 | No write occurs and the correct store/location is shown. |
| [ ] | T-14 | Create one sacrificial draft product with images | L | S-15 | All product, variant, inventory, and image fields are correct. |
| [ ] | T-15 | Rerun the same item and verify no duplicate | M | S-21 | The existing SKU/status is detected. |
| [ ] | T-16 | Simulate interruption mid-upload | L | S-16,S-20 | The next run resumes safely. |
| [ ] | T-17 | Run a 10-item Shopify draft test | L | S-23 | Ten correct drafts are created with zero mismatched media. |
| [ ] | T-18 | Run a real 20-tape physical pilot | L | P-14,I-20,D-10 | Every tape, item row, and photo group matches. |
| [ ] | T-19 | Randomly retrieve all 20 pilot tapes | M | T-18 | Every tape is found from its record. |
| [ ] | T-20 | Run a 100-tape production pilot | XL | T-17,T-19 | The workflow operates at meaningful scale. |
| [ ] | T-21 | Retrieve ten random 100-tape pilot items | M | T-20 | All ten are found and match exact photos where required. |
| [ ] | T-22 | Measure and approve production readiness | M | T-20,T-21 | Time, error, and throughput targets are met. |

## Track B — Backup, Security, and Recovery

| Status | ID | Task | Size | Prerequisites | Done when |
| --- | --- | --- | --- | --- | --- |
| [ ] | B-01 | Obtain and label an external backup drive | M | — | A separate device has sufficient capacity. |
| [ ] | B-02 | Define retention for originals, processed copies, DB, and CSVs | S | A-01 | Deletion rules are written. |
| [ ] | B-03 | Back up the SQLite database automatically | M | D-15 | A timestamped copy is created before risky operations. |
| [ ] | B-04 | Synchronize new originals and processed files to backup | L | B-01,E-10 | A repeatable copy/sync command exists. |
| [ ] | B-05 | Verify backups by file count/hash | M | I-14,B-04 | Backup integrity is checked. |
| [ ] | B-06 | Keep Shopify tokens out of Git, CSVs, and logs | S | S-04 | Secret scanning finds no exposed token. |
| [ ] | B-07 | Mask secrets in errors and debug logs | M | S-04 | Logs cannot expose authentication values. |
| [ ] | B-08 | Create database restore instructions | M | B-03 | A test database can be restored. |
| [ ] | B-09 | Create full application disaster-recovery instructions | M | E-14,B-04 | A new machine can be rebuilt from repository and backups. |
| [ ] | B-10 | Perform a recovery drill | L | B-08,B-09 | A disposable environment restores test data successfully. |

## Track O — Standard Operations

| Status | ID | Task | Size | Prerequisites | Done when |
| --- | --- | --- | --- | --- | --- |
| [ ] | O-01 | Print a one-page booth cheat sheet | S | A-03,P-14 | The QR sequence and photo order are visible at the booth. |
| [ ] | O-02 | Finalize the batch photography SOP after the real 20-tape pilot | M | T-18 | The SOP reflects actual use. |
| [ ] | O-03 | Define phone-photo deletion rule | S | B-02 | Photos remain until import, verification, and backup are complete. |
| [ ] | O-04 | Define shelf-transfer procedure | M | D-03 | Moving a tape requires a location update. |
| [ ] | O-05 | Define Q1 quarantine and clearance procedure | M | P-09,D-11 | Contaminated or uncertain items cannot enter listed stock. |
| [ ] | O-06 | Define returned-item procedure | M | O-05 | Returns enter review before returning to stock. |
| [ ] | O-07 | Define duplicate/pooled copy procedure | M | A-09,D-12 | Copies are pooled only when commercially interchangeable. |
| [ ] | O-08 | Define draft review and publish procedure | M | S-24 | A person verifies title, price, images, and condition before publication. |
| [ ] | O-09 | Define order-picking and failed-pick procedure | M | T-21 | Shelf/photo search and discrepancy escalation are documented. |
| [ ] | O-10 | Review workflow metrics after every 500 tapes | M | T-22 | Improvements are based on measured bottlenecks. |

## Track AI — Deferred Enhancements

| Status | ID | Task | Size | Prerequisites | Done when |
| --- | --- | --- | --- | --- | --- |
| [ ] | AI-01 | Define AI suggestion fields and prohibited decisions | M | T-22 | AI may suggest but cannot publish or set location. |
| [ ] | AI-02 | Add barcode extraction | L | AI-01 | UPC candidates appear beside manual fields. |
| [ ] | AI-03 | Add OCR title/distributor extraction | L | AI-01 | Text suggestions reduce typing. |
| [ ] | AI-04 | Add vision title/edition suggestions | L | AI-01 | Ambiguous results route to review. |
| [ ] | AI-05 | Add existing-catalog matching | XL | AI-02,AI-03,AI-04 | Duplicate candidates are ranked with evidence. |
| [ ] | AI-06 | Benchmark accuracy and cost on 100 confirmed items | L | AI-02,AI-03,AI-04 | Automation is measured before auto-acceptance. |
| [ ] | AI-07 | Evaluate true Shopify bulk operations | L | T-22 | Only adopted if the controlled queue is a measured bottleneck. |
| [ ] | AI-08 | Evaluate eBay/product-research tools separately | L | T-22 | Pricing work is scoped without blocking inventory intake. |

# Part V — Production Acceptance Gate

[ ] Current QR cards decode in the real booth.

[ ] The parser uses NEXT boundaries only and correctly groups a real 100-tape batch.

[ ] Every item receives one stable Item ID / SKU.

[ ] The first image is F and all optional images are numbered.

[ ] Original images are preserved and backed up.

[ ] CSV edits round-trip by Item ID without mismatch.

[ ] Shopify dry-run blocks incomplete and duplicate items.

[ ] The uploader creates drafts and directly uploads the correct local images.

[ ] Rerunning does not duplicate successful products.

[ ] Ten random physical tapes can be retrieved from their shelf/photo records.

[ ] No physical tape is disconnected from its local record or Shopify draft.

# Technical References

Shopify GraphQL Admin API

Shopify productCreate

Shopify productSet

Shopify stagedUploadsCreate

Shopify fileCreate

Shopify API limits

Shopify bulk imports (deferred)